## Read Me
RFI Tracker
Agentic Procurement ¦ Internal - do not share vendor data outside Agentic ¦ Owner: Jason Knedlhans
Version | 1.0
Version date | 2026-10-05
Live file | RFI-Tracker.xlsx in the Procurement SharePoint library (AI Procurement > artifacts > rfi-tracker). Always open it from SharePoint; do not keep local copies.
Status | In review
PURPOSE
What | One file for every RFI activity. Each RFI activity is its own tab, tied to one project and one vendor type, and lists the invited vendors with contacts, RFI status, last contact, qualification status, key item responses and ratings, and the next action, owner and date.
TABS
Dashboard | Live totals by vendor type and by project.
RFI Register | Index of all RFI activities. Type the RFI ID; the rest fills from that tab.
RFI-001 | Example RFI (BESS vendors, placeholder project). Repurpose it for the first real RFI or delete it and its Register row.
RFI_TEMPLATE | Blank RFI tab. Copy it for each new RFI activity; never type data into the template itself.
Vendors | Master vendor and contact list. RFI tabs pull contacts from here, so update contacts here only.
Key Items | Default 5-7 key items per vendor type (10 slots). Drives the key item headers on RFI tabs.
Projects | Project list for the Project dropdown. Rename the placeholders.
Lists | Dropdown values (statuses, ratings, owners).
Change Log | Record of structural changes and new RFI tabs.
ADD A NEW RFI ACTIVITY
1. Copy the template | Right-click the RFI_TEMPLATE tab > Move or Copy > tick Create a copy > OK. (Excel for the web: right-click > Duplicate.)
2. Rename the tab | Use the next RFI ID, e.g. RFI-002. Keep it short, no spaces.
3. Fill the header | C3 RFI ID (same as tab name), C4 Project, C5 Vendor Type, title, owner, dates, status. Key item headers fill automatically from the vendor type.
4. Add vendors | Pick vendors in column A (dropdown from the Vendors tab). Add a missing vendor to the Vendors tab first.
5. Register it | Type the RFI ID in the next empty row of the RFI Register, then add a Change Log line.
KEY ITEMS
Change a header | For this RFI only: type over the header in row 13 of the RFI tab. For all RFIs of a vendor type: edit the Key Items tab.
Add a key item | Type a name into a spare slot (shown as 'spare - type a name'), either on the RFI tab or on the Key Items tab.
Rating | Meets / Review / Risk / Fails / Not Rated. Fails and Review / Risk roll up to the tab summary, Register and Dashboard.
CELL COLORS
Yellow | Enter or edit data.
Grey | Formula. Do not overwrite (exception: key item headers in row 13).
Red / amber | Overdue actions, Fails ratings, or a Register row whose tab name does not match.
VERSION CONTROL
Live file | One file, one name, one link. Everyone edits the SharePoint copy in place (co-authoring with AutoSave on). Do not download, edit offline and re-upload, and do not Save As a new name.
Version history | SharePoint keeps every saved version automatically. To see or restore: File > Info > Version History (desktop) or the file's ... menu > Version history (SharePoint).
Version number | Major (2.0): structural change - new or removed columns, tabs other than new RFI tabs, formula changes. Minor (1.1): list or key item default changes, new RFI tab. Update the Version cell above and add a Change Log line for both.
Snapshots | Before a major version, save a dated copy to artifacts/archive/rfi-tracker/ (e.g. 2026-10-05_rfi-tracker_v1.0.xlsx).
Data entry | Routine updates (statuses, dates, responses) need no Change Log line; version history records them.
DATA NOTES / RISKS
Vendor data | Vendors tab seeded 2026-10-05 from the vendor landscape tracker. It is AI-seeded from public sources and unverified; no named contacts yet. Mark Data Verified? = Yes once confirmed with the vendor.
Two vendor lists | The vendor landscape tracker also holds vendors. Treat this file's Vendors tab as the contact record for RFIs, or agree another system of record.
Confidentiality | Internal. Vendor responses may include pricing or confidential data; do not share outside Agentic.
Tab names | Register formulas find RFI tabs by name. Renaming a tab breaks its Register row (shows 'Tab not found' in red) until the RFI ID in column A is updated.

## Dashboard
Dashboard
Live totals from the RFI Register. Closed and cancelled RFIs are excluded from Active RFIs.
Active RFIs | Total RFIs | Vendors invited | RFIs sent | Responses | Actions overdue | Key item fails
1 | 1 | 10 | 0 | 0 | 0 | 0
By vendor type
Vendor Type | RFIs | Active | Vendors Invited | Responses | Actions Overdue | Key Item Fails
Environmental Engineering | 0 | 0 | 0 | 0 | 0 | 0
Civil Engineering | 0 | 0 | 0 | 0 | 0 | 0
Structural Engineering | 0 | 0 | 0 | 0 | 0 | 0
Electrical Engineering | 0 | 0 | 0 | 0 | 0 | 0
Fire Protection Engineering | 0 | 0 | 0 | 0 | 0 | 0
Owner's Engineer | 0 | 0 | 0 | 0 | 0 | 0
Engineer of Record | 0 | 0 | 0 | 0 | 0 | 0
Independent Engineer | 0 | 0 | 0 | 0 | 0 | 0
BESS Equipment | 1 | 1 | 10 | 0 | 0 | 0
MV Transformers | 0 | 0 | 0 | 0 | 0 | 0
HV Breakers | 0 | 0 | 0 | 0 | 0 | 0
MV Breakers / Switchgear | 0 | 0 | 0 | 0 | 0 | 0
EPC Contractor | 0 | 0 | 0 | 0 | 0 | 0
Software | 0 | 0 | 0 | 0 | 0 | 0
By project
Project | RFIs | Active | Vendors Invited | Responses | Actions Overdue | Key Item Fails
Seven Angels BESS | 0 | 0 | 0 | 0 | 0 | 0
Project B (placeholder - rename) | 0 | 0 | 0 | 0 | 0 | 0
Project C (placeholder - rename) | 0 | 0 | 0 | 0 | 0 | 0

## RFI Register
RFI Register
One row per RFI activity. Type the RFI ID (= tab name) in column A; the grey columns fill in from that tab. Add the outcome and notes in yellow.
RFI ID (tab name) | Project | Vendor Type | RFI Title / Scope | RFI Owner | Issue Date | Response Due | Activity Status | Vendors Invited | RFIs Sent | Responses | Actions Overdue | Key Items Fails | Days to Due | Outcome / Next RFx Step | Notes
RFI-001 | Project A (placeholder - rename) | BESS Equipment | EXAMPLE - BESS equipment RFI (repurpose or delete) | Jason Knedlhans |  |  | Planning | 10 | 0 | 0 | 0 | 0 |  |  | Example tab - repurpose for the first real RFI or delete this row and the tab.

## RFI-001
RFI-001 ¦ EXAMPLE - BESS equipment RFI (repurpose or delete)
Yellow = enter data. Grey = formula, do not overwrite (except key item headers in row 13, which you may type over). Rename this tab to match the RFI ID, then add the ID to the RFI Register.
| RFI ID | RFI-001 |  |  |  |  | Vendors invited | 10
| Project | Project A (placeholder - rename) |  |  |  |  | RFIs sent | 0
| Vendor Type | BESS Equipment |  |  |  |  | Responses received | 0
| RFI Title / Scope | EXAMPLE - BESS equipment RFI (repurpose or delete) |  |  |  |  | Declined / no response | 0
| RFI Owner | Jason Knedlhans |  |  |  |  | Actions overdue | 0
| Issue Date | [5 empty] | Key items: Review / Risk | 9
| Response Due | [5 empty] | Key items: Fails | 0
| Activity Status | Planning |  |  |  |  | Days to response due
VENDOR & CONTACT (contacts pull from Vendors tab) |  |  |  |  | RFI |  |  |  |  | KEY ITEMS - BESS EQUIPMENT | [19 empty] | NEXT ACTION
Vendor | Vendor ID | Contact Name | Contact Email | Contact Phone | RFI Status | Date Sent | Last Contact | Response Date | Qualification Status | Lead time (weeks ARO) |  | FEOC compliance |  | Cell chemistry & cell / module origin |  | Certifications (UL 9540, UL 9540A, NFPA 855) |  | Warranty & performance guarantee |  | Domestic content (ITC adder) |  | Bankability / financial strength |  | Key item 8 (spare - type a name) |  | Key item 9 (spare - type a name) |  | Key item 10 (spare - type a name) |  | Next Action | Next Action Owner | Next Action Date | Action Flag | Notes
[10 empty] | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating
Tesla (Tesla Energy) | BESS-001 |  |  |  | Not Sent |  |  |  | Discovery |  |  | Flagged FEOC Review in vendor landscape - confirm ownership / origin in RFI | Review / Risk | [16 empty] | Identify RFI contact | Jason Knedlhans
Fluence Energy | BESS-002 |  |  |  | Not Sent |  |  |  | Discovery |  |  | Flagged FEOC Review in vendor landscape - confirm ownership / origin in RFI | Review / Risk | [16 empty] | Identify RFI contact | Jason Knedlhans
Sungrow | BESS-003 |  |  | +1 833 747 6937 | Not Sent |  |  |  | Discovery |  |  | Flagged FEOC Review in vendor landscape - confirm ownership / origin in RFI | Review / Risk | [16 empty] | Identify RFI contact | Jason Knedlhans
LG Energy Solution Vertech | BESS-004 |  |  |  | Not Sent |  |  |  | Discovery |  |  | Flagged FEOC Review in vendor landscape - confirm ownership / origin in RFI | Review / Risk | [16 empty] | Identify RFI contact | Jason Knedlhans
Samsung SDI | BESS-005 |  |  |  | Not Sent |  |  |  | Discovery | [20 empty] | Identify RFI contact | Jason Knedlhans
Wärtsilä Energy Storage | BESS-006 |  |  | +1 281 233 6200 | Not Sent |  |  |  | Discovery |  |  | Flagged FEOC Review in vendor landscape - confirm ownership / origin in RFI | Review / Risk | [16 empty] | Identify RFI contact | Jason Knedlhans
FlexGen Power Systems | BESS-007 |  |  | 855-327-5674 | Not Sent |  |  |  | Discovery |  |  | Flagged FEOC Review in vendor landscape - confirm ownership / origin in RFI | Review / Risk | [16 empty] | Identify RFI contact | Jason Knedlhans
Hithium | BESS-008 |  |  |  | Not Sent |  |  |  | Discovery |  |  | Flagged FEOC Review in vendor landscape - confirm ownership / origin in RFI | Review / Risk | [16 empty] | Identify RFI contact | Jason Knedlhans
Canadian Solar e-STORAGE | BESS-009 |  |  |  | Not Sent |  |  |  | Discovery |  |  | Flagged FEOC Review in vendor landscape - confirm ownership / origin in RFI | Review / Risk | [16 empty] | Identify RFI contact | Jason Knedlhans
Prevalon Energy (now Nextpower) | BESS-010 |  |  |  | Not Sent |  |  |  | Discovery |  |  | Flagged FEOC Review in vendor landscape - confirm ownership / origin in RFI | Review / Risk | [16 empty] | Identify RFI contact | Jason Knedlhans
Note on C3: Must match this tab's name exactly (e.g. RFI-002)
Note on C4: Pick from Projects tab
Note on C5: Sets the default key item headers
Note on C8: yyyy-mm-dd
Note on C9: yyyy-mm-dd

## RFI_TEMPLATE
RFI Activity (new - fill in the yellow cells)
Yellow = enter data. Grey = formula, do not overwrite (except key item headers in row 13, which you may type over). Rename this tab to match the RFI ID, then add the ID to the RFI Register.
| RFI ID | [5 empty] | Vendors invited | 0
| Project | [5 empty] | RFIs sent | 0
| Vendor Type | [5 empty] | Responses received | 0
| RFI Title / Scope | [5 empty] | Declined / no response | 0
| RFI Owner | [5 empty] | Actions overdue | 0
| Issue Date | [5 empty] | Key items: Review / Risk | 0
| Response Due | [5 empty] | Key items: Fails | 0
| Activity Status | [5 empty] | Days to response due
VENDOR & CONTACT (contacts pull from Vendors tab) |  |  |  |  | RFI |  |  |  |  | KEY ITEMS - pick a Vendor Type in C5 | [19 empty] | NEXT ACTION
Vendor | Vendor ID | Contact Name | Contact Email | Contact Phone | RFI Status | Date Sent | Last Contact | Response Date | Qualification Status | Key item 1 |  | Key item 2 |  | Key item 3 |  | Key item 4 |  | Key item 5 |  | Key item 6 |  | Key item 7 |  | Key item 8 |  | Key item 9 |  | Key item 10 |  | Next Action | Next Action Owner | Next Action Date | Action Flag | Notes
[10 empty] | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating | Response / notes | Rating
Note on C3: Must match this tab's name exactly (e.g. RFI-002)
Note on C4: Pick from Projects tab
Note on C5: Sets the default key item headers
Note on C8: yyyy-mm-dd
Note on C9: yyyy-mm-dd

## Vendors
Vendors
Master vendor and contact list. RFI tabs look up contacts here, so update contacts in this tab only. Seeded 2026-10-05 from vendor landscape tracker (AI-seeded, unverified).
Vendor ID | Vendor Name | Vendor Type | Services / Product Line | Website | Main Phone | Contact Page | Primary Contact | Contact Title | Contact Email | Direct Phone | Qualification Status | Data Verified? | Notes
ENV-001 | ERM (Environmental Resources Management) | Environmental Engineering | Environmental, health, safety, risk and social consulting; permitting/impact assessment and sustainability services for energy projects | https://www.erm.com/ |  | https://www.erm.com/contact-us/ |  |  |  |  | Discovery | No - AI seeded
ENV-002 | Tetra Tech, Inc. | Environmental Engineering | Environmental consulting and engineering (water, environment, energy); permitting, site assessment, natural/cultural resources | https://www.tetratech.com/ | +1 (626) 351-4664 | https://www.tetratech.com/contact/ |  |  |  |  | Discovery | No - AI seeded
ENV-003 | Stantec Inc. | Environmental Engineering | Environmental consulting and engineering; environmental permitting and studies for energy/infrastructure projects | https://www.stantec.com/en | [6 empty] | Discovery | No - AI seeded
ENV-004 | WSP Global Inc. (WSP USA) | Environmental Engineering | Environmental, engineering and permitting consulting; power & energy platform (incl. POWER Engineers and TRC) | https://www.wsp.com/en-us |  | https://www.wsp.com/en-us/contact-us |  |  |  |  | Discovery | No - AI seeded
ENV-005 | Terracon Consultants, Inc. | Environmental Engineering | Environmental site assessment (Phase I/II ESA), geotechnical, materials testing and facilities consulting | https://www.terracon.com/ | (800) 593-7777 | https://www.terracon.com/contact/ |  |  |  |  | Discovery | No - AI seeded
ENV-006 | SWCA Environmental Consultants | Environmental Engineering | Environmental planning/permitting, natural & cultural resources, renewable energy environmental services | https://www.swca.com/ | 602-274-3831 | https://www.swca.com/contact/ |  |  |  |  | Discovery | No - AI seeded
ENV-007 | Westwood Professional Services | Environmental Engineering | Renewable/BESS development support incl. environmental permitting, survey, and design of standalone and hybrid battery storage | https://westwoodps.com/ | 214-473-4640 (HQ); 1-888-937-5150 (toll-free) | https://westwoodps.com/contact-us |  |  |  |  | Discovery | No - AI seeded
ENV-008 | HDR, Inc. | Environmental Engineering | Engineering, environmental and architecture consulting incl. environmental planning for infrastructure/energy | https://www.hdrinc.com/ | (402) 399-1000 | https://www.hdrinc.com/contact-us |  |  |  |  | Discovery | No - AI seeded
CIV-001 | Kimley-Horn and Associates, Inc. | Civil Engineering | Site civil, grading/drainage, roads and planning/design; energy and infrastructure site development | https://www.kimley-horn.com/ |  | https://www.kimley-horn.com/contact/ |  |  |  |  | Discovery | No - AI seeded
CIV-002 | Westwood Professional Services | Civil Engineering | Civil/site design, survey, and permitting for utility-scale solar, wind and BESS; power delivery | https://westwoodps.com/ | 214-473-4640 (HQ); 1-888-937-5150 (toll-free) | https://westwoodps.com/contact-us |  |  |  |  | Discovery | No - AI seeded
CIV-003 | Halff Associates, Inc. | Civil Engineering | Infrastructure consulting: site civil, drainage/water resources, survey, transportation | https://www.halff.com/ |  | https://www.halff.com/contact/ |  |  |  |  | Discovery | No - AI seeded
CIV-004 | Pape-Dawson Engineers | Civil Engineering | Civil engineering, survey, permitting; substation/switchyard civil design (170+ substations) and wind/solar civil | https://www.pape-dawson.com/ | 210-375-9000 | https://www.pape-dawson.com/contact |  |  |  |  | Discovery | No - AI seeded
CIV-005 | Bowman Consulting Group Ltd. | Civil Engineering | Infrastructure design, civil engineering, survey, environmental; energy design incl. battery storage | https://bowman.com/ | (703) 464-1000 | https://bowman.com/contact |  |  |  |  | Discovery | No - AI seeded
CIV-006 | Terracon Consultants, Inc. | Civil Engineering | Geotechnical engineering, materials testing and construction QA for site/foundation design | https://www.terracon.com/ | (800) 593-7777 | https://www.terracon.com/contact/ |  |  |  |  | Discovery | No - AI seeded
CIV-007 | Burns & McDonnell | Civil Engineering | Engineering/EPC incl. site civil for power generation, substations and transmission | https://www.burnsmcd.com/ |  | https://info.burnsmcd.com/contact-us |  |  |  |  | Discovery | No - AI seeded
STR-001 | Walter P Moore | Structural Engineering | Structural and civil engineering, foundations, forensic engineering | https://www.walterpmoore.com/ | 800-364-7300 (general); 713-630-7300 (Houston HQ) | https://www.walterpmoore.com/contact |  |  |  |  | Discovery | No - AI seeded
STR-002 | Sargent & Lundy | Structural Engineering | Power engineering incl. structural design for generation, BESS, substations and transmission structures | https://www.sargentlundy.com/ | (312) 269-2000 | https://www.sargentlundy.com/contact-us |  |  |  |  | Discovery | No - AI seeded
STR-003 | Burns & McDonnell | Structural Engineering | Structural/civil design for substations, equipment foundations and power plants (engineering/EPC) | https://www.burnsmcd.com/ |  | https://info.burnsmcd.com/contact-us |  |  |  |  | Discovery | No - AI seeded
STR-004 | Black & Veatch | Structural Engineering | Engineering/EPC for power generation, power delivery and substations incl. structural design | https://www.bv.com/ | +1 913-458-2000 | https://www.bv.com/contact-us |  |  |  |  | Discovery | No - AI seeded
STR-005 | POWER Engineers (a WSP company) | Structural Engineering | Power delivery engineering incl. substation and transmission structural/civil design; renewables & storage | https://www.powereng.com/ | [6 empty] | Discovery | No - AI seeded
STR-006 | Electrical Consultants, Inc. (ECI) | Structural Engineering | Power delivery only: civil, structural, electrical, survey for substations, transmission (to 765 kV), renewables and battery storage | https://eciusa.com/ | [6 empty] | Discovery | No - AI seeded
ELE-001 | POWER Engineers (a WSP company) | Electrical Engineering | Substation, transmission and interconnection engineering; renewables & storage power delivery | https://www.powereng.com/ | [6 empty] | Discovery | No - AI seeded
ELE-002 | Burns & McDonnell | Electrical Engineering | Substation/transmission design and EPC, interconnection and power generation electrical engineering | https://www.burnsmcd.com/ |  | https://info.burnsmcd.com/contact-us |  |  |  |  | Discovery | No - AI seeded
ELE-003 | Sargent & Lundy | Electrical Engineering | Grid/substation/transmission engineering, renewables and BESS electrical design, owner's engineer/due diligence | https://www.sargentlundy.com/ | (312) 269-2000 | https://www.sargentlundy.com/contact-us |  |  |  |  | Discovery | No - AI seeded
ELE-004 | Black & Veatch | Electrical Engineering | Power delivery (substation/transmission) engineering and EPC; generation and storage | https://www.bv.com/ | +1 913-458-2000 | https://www.bv.com/contact-us |  |  |  |  | Discovery | No - AI seeded
ELE-005 | Electric Power Engineers, LLC (EPE) | Electrical Engineering | Grid analysis/interconnection studies, utility engineering, regulatory/compliance; renewables & storage | https://epeconsulting.com/ | 512-382-6700 | https://epeconsulting.com/contact |  |  |  |  | Discovery | No - AI seeded
ELE-006 | TRC Companies, Inc. (a member of WSP) | Electrical Engineering | Power & utilities engineering incl. substation, transmission and interconnection; environmental | https://www.trccompanies.com/ | +1 (860) 298-9692 | https://www.trccompanies.com/contact-us/ |  |  |  |  | Discovery | No - AI seeded
ELE-007 | Leidos (Power Delivery / Energy) | Electrical Engineering | Substation design (4-765 kV), T&D lines, SCADA, system planning, NERC compliance for Texas utilities | https://www.leidos.com/ |  | https://www.leidos.com/contact-us |  |  |  |  | Discovery | No - AI seeded
ELE-008 | Electrical Consultants, Inc. (ECI) | Electrical Engineering | Power delivery engineering: substations, transmission to 765 kV, protection & control, renewables/BESS | https://eciusa.com/ | [6 empty] | Discovery | No - AI seeded
FIRE-001 | Jensen Hughes | Fire Protection Engineering | Lithium-ion/BESS risk consulting: hazard mitigation, NFPA 855/UL 9540A expertise, explosion protection (CFD, deflagration venting), large-scale fire testing | https://www.jensenhughes.com/ |  | https://www.jensenhughes.com/contact-us |  |  |  |  | Discovery | No - AI seeded
FIRE-002 | ESRG (Energy Safety Response Group) | Fire Protection Engineering | Energy-storage-only safety: testing, permitting/project review, emergency response plans & first-responder training, incident response | https://www.energyresponsegroup.com/ | 1-833-SAFE-ESS | https://www.energyresponsegroup.com/contact |  |  |  |  | Discovery | No - AI seeded
FIRE-003 | Fire & Risk Alliance | Fire Protection Engineering | BESS code consulting (NFPA 855/IFC), HMA, UL 9540A assessment, deflagration (NFPA 68/69) and heat-flux modeling, FMEA, ERP and responder training | https://fireriskalliance.com/ | (301) 658-3060 | https://fireriskalliance.com/contact-us/ |  |  |  |  | Discovery | No - AI seeded
FIRE-004 | Telgian Engineering & Consulting | Fire Protection Engineering | Fire protection engineering and code consulting; has published ESS fire-hazard guidance (BESS-specific services not detailed on site) | https://www.telgian.com/ | 480.753.5444 | https://www.telgian.com/contact/ |  |  |  |  | Discovery | No - AI seeded
FIRE-005 | DNV | Fire Protection Engineering | Battery safety, risk analysis (QRA) and permitting support; energy storage technical due diligence and engineering review | https://www.dnv.com/ |  | https://www.dnv.us/contact/ |  |  |  |  | Discovery | No - AI seeded
FIRE-006 | UL Solutions Inc. | Fire Protection Engineering | UL 9540A testing, NFPA 855 documentation readiness review, fire/explosion hazard assessment, AHJ-focused technical support | https://www.ul.com/ | +1.877.854.3577 (customer service) | https://www.ul.com/contact-us |  |  |  |  | Discovery | No - AI seeded
FIRE-007 | Exponent, Inc. | Fire Protection Engineering | BESS safety & risk consulting: fire protection engineering, emergency response planning, root-cause failure analysis, testing | https://www.exponent.com/ | (650) 326-9400 | [5 empty] | Discovery | No - AI seeded
OE-001 | DNV | Owner's Engineer | Owner's engineering for energy storage: feasibility, dispatch modeling, RFP/tender support, design and procurement review, grid connection, warranty definition, FAT/SAT, construction PM, HSE | https://www.dnv.com | +1 281 396 1000 (DNV North America HQ, Houston) | https://www.dnv.us/contact/ |  |  |  |  | Discovery | No - AI seeded
OE-002 | Enertis Applus+ | Owner's Engineer | Renewables and BESS technical advisory: design evaluation, site assessment, engineering, QA/QC, testing and optimization for developers, owners and financiers | https://enertisapplus.com | +1 415 671 4000 (US offices, San Francisco / Raleigh) | https://enertisapplus.com/contact/ |  |  |  |  | Discovery | No - AI seeded
OE-003 | Black & Veatch | Owner's Engineer | BESS owner's engineer: EPC design review, construction monitoring, commissioning supervision, early operations oversight; firm reports 74 GWh supported as OE | https://www.bv.com | +1 913-458-2000 | https://www.bv.com/contact-us |  |  |  |  | Discovery | No - AI seeded
OE-004 | Sargent & Lundy | Owner's Engineer | Owner's engineer for utility-scale solar + BESS: EPC RFP/specs, bid evaluation, contract negotiation support, review of LV/MV, collection, substation and transmission designs | https://www.sargentlundy.com | 312-269-2000 | https://www.sargentlundy.com/contact-us |  |  |  |  | Discovery | No - AI seeded
OE-005 | Clean Energy Associates (Intertek CEA) | Owner's Engineer | Owner's engineer and technical due diligence; storage system QA, factory/production monitoring, supply-chain traceability for BESS and PV | https://www.cea3.com | [6 empty] | Discovery | No - AI seeded
OE-006 | Kimley-Horn | Owner's Engineer | BESS consulting incl. owner's engineering, feasibility, siting/permitting, interconnection studies, and civil/structural/electrical design | https://www.kimley-horn.com |  | https://www.kimley-horn.com/contact/submit-a-service-inquiry/ |  |  |  |  | Discovery | No - AI seeded
OE-007 | Natural Power | Owner's Engineer | Renewables-only consultant: owner's advisory, technology evaluation, field inspections and technical due diligence for standalone/co-located storage | https://www.naturalpower.com | +1 (518) 308 0200 (Saratoga Springs, NY office) | https://www.naturalpower.com/us/contact |  |  |  |  | Discovery | No - AI seeded
EOR-001 | Burns & McDonnell | Engineer of Record | In-house design engineering and EPC for BESS, substations and transmission; delivered Texas BESS EPC (e.g., RWE Texas Waves II, LGES/SER West Texas) | https://www.burnsmcd.com | (816) 333-9400 | https://info.burnsmcd.com/contact-us |  |  |  |  | Discovery | No - AI seeded
EOR-002 | Sargent & Lundy | Engineer of Record | Power engineering firm: electrical design for collection, substation and transmission; renewables and storage engineering | https://www.sargentlundy.com | 312-269-2000 | https://www.sargentlundy.com/contact-us |  |  |  |  | Discovery | No - AI seeded
EOR-003 | POWER Engineers (Member of WSP) | Engineer of Record | Power delivery engineering: substation, transmission, renewables and storage design | https://www.powereng.com | [6 empty] | Discovery | No - AI seeded
EOR-004 | Westwood Professional Services | Engineer of Record | Design, permitting and optimization of standalone/hybrid BESS; substation and transmission line engineering; surveying | https://www.westwoodps.com | 1-888-937-5150 | https://westwoodps.com/contact-us |  |  |  |  | Discovery | No - AI seeded
EOR-005 | Black & Veatch | Engineer of Record | Engineering and EPC for BESS and HV substations; firm reports 8.9 GWh delivered as BESS EPC | https://www.bv.com | +1 913-458-2000 | https://www.bv.com/contact-us |  |  |  |  | Discovery | No - AI seeded
EOR-006 | Kimley-Horn | Engineer of Record | Detailed civil, structural and electrical BESS design incl. plant, HV substation and transmission/interconnection design | https://www.kimley-horn.com |  | https://www.kimley-horn.com/contact/submit-a-service-inquiry/ |  |  |  |  | Discovery | No - AI seeded
EOR-007 | Bowman Consulting Group | Engineer of Record | Energy design and engineering incl. BESS, electric power and transmission; civil/survey | https://bowman.com |  | https://bowman.com/contact/ |  |  |  |  | Discovery | No - AI seeded
IE-001 | DNV | Independent Engineer | Independent engineering and technical due diligence for BESS: vendor/design/safety review, performance validation, guarantee verification, bankability for investors/financiers | https://www.dnv.com | +1 281 396 1000 (DNV North America HQ, Houston) | https://www.dnv.us/contact/ |  |  |  |  | Discovery | No - AI seeded
IE-002 | Enertis Applus+ | Independent Engineer | Lender's IE for BESS: project-finance technical due diligence, design/grid/warranty review, MC/SC/FC milestone certification (e.g., 550 MW / 1,433 MWh Texas portfolio for Excelsior/Lydian) | https://enertisapplus.com | +1 415 671 4000 (US offices) | https://enertisapplus.com/contact/ |  |  |  |  | Discovery | No - AI seeded
IE-003 | Leidos | Independent Engineer | Independent engineering for project development, acquisition, financing and investment diligence across energy storage and other technologies | https://www.leidos.com | (571) 526-6000 | https://www.leidos.com/contact |  |  |  |  | Discovery | No - AI seeded
IE-004 | Sargent & Lundy | Independent Engineer | BESS independent engineering due diligence for investors/tax equity: use-case modeling, module warranty terms, fire protection design | https://www.sargentlundy.com | 312-269-2000 | https://www.sargentlundy.com/contact-us |  |  |  |  | Discovery | No - AI seeded
IE-005 | Natural Power | Independent Engineer | Independent engineering and technical due diligence for lenders/investors on wind, solar and storage; new Head of IE North America (Dec 2025) | https://www.naturalpower.com | +1 (518) 308 0200 (Saratoga Springs, NY office) | https://www.naturalpower.com/us/contact |  |  |  |  | Discovery | No - AI seeded
IE-006 | UL Solutions | Independent Engineer | Energy Storage Advisory: IE and technical advisory for project financing, tax equity, sales and acquisitions (contracts, financial models, designs); BESS testing/certification | https://www.ul.com | (847) 272-8800 | [5 empty] | Discovery | No - AI seeded
BESS-001 | Tesla (Tesla Energy) | BESS Equipment | Megapack 2 / Megapack 2 XL / Megapack 3 (~5 MWh) / Megablock (4x Megapack 3 + transformer + switchgear, ~20 MWh) | https://www.tesla.com/megapack |  | https://www.tesla.com/megapack |  |  |  |  | Discovery | No - AI seeded | Landscape: FEOC Review
BESS-002 | Fluence Energy | BESS Equipment | Grid-scale BESS (Gridstack/Smartstack platforms), US domestic-content offering | https://fluenceenergy.com | [6 empty] | Discovery | No - AI seeded | Landscape: FEOC Review
BESS-003 | Sungrow | BESS Equipment | PowerTitan 3.0 AC block (6.9 MWh per 20-ft container); PowerStack (C&I) | https://www.sungrowpower.com/us/en | +1 833 747 6937 | https://www.sungrowpower.com/us/en/about-us/contact-us |  |  |  |  | Discovery | No - AI seeded | Landscape: FEOC Review
BESS-004 | LG Energy Solution Vertech | BESS Equipment | Containerized LFP grid-scale BESS + AEROS controls/analytics; integration and lifecycle services | [7 empty] | Discovery | No - AI seeded | Landscape: FEOC Review
BESS-005 | Samsung SDI | BESS Equipment | Samsung Battery Box (SBB) 2.0 — prismatic LFP DC block (cell/DC supplier; requires PCS/EMS integrator) | https://www.samsungsdi.com | [6 empty] | Discovery | No - AI seeded
BESS-006 | Wärtsilä Energy Storage | BESS Equipment | Quantum3 AC-block BESS (introduced Sep 2024); GEMS software | https://www.wartsila.com/usa | +1 281 233 6200 | https://www.wartsila.com/usa/about/contact-us |  |  |  |  | Discovery | No - AI seeded | Landscape: FEOC Review
BESS-007 | FlexGen Power Systems | BESS Equipment | BESS integration with HybridOS EMS; legacy Powin fleet support (Powin assets/IP acquired) | https://www.flexgen.com | 855-327-5674 | https://www.flexgen.com/contact-us |  |  |  |  | Discovery | No - AI seeded | Landscape: FEOC Review
BESS-008 | Hithium | BESS Equipment | LFP BESS modules/systems (∞Power 6.25 MWh platform) | https://hithium.com | [6 empty] | Discovery | No - AI seeded | Landscape: FEOC Review
BESS-009 | Canadian Solar e-STORAGE | BESS Equipment | Utility-scale BESS (SolBank platform) and EPC/LTSA services | https://www.csisolar.com/e-storage/ | [6 empty] | Discovery | No - AI seeded | Landscape: FEOC Review
BESS-010 | Prevalon Energy (now Nextpower) | BESS Equipment | HD5 AC / HD5 DC BESS platforms, insightOS, service/LTSA | https://prevalonenergy.com |  | https://prevalonenergy.com/contact-us/ |  |  |  |  | Discovery | No - AI seeded | Landscape: FEOC Review
MVT-001 | Hitachi Energy | MV Transformers | Pad-mount and distribution transformers (single-phase pad-mount from Reynosa); large distribution transformers (South Boston, VA) | https://www.hitachienergy.com/us/en | [6 empty] | Discovery | No - AI seeded
MVT-002 | Eaton | MV Transformers | Three-phase pad-mount transformers; single-phase/pole/pad-mount | https://www.eaton.com/us/en-us.html | [6 empty] | Discovery | No - AI seeded
MVT-003 | Prolec GE (GE Vernova) | MV Transformers | Three-phase pad-mount (Shreveport) and medium power / substation transformers (Goldsboro) | https://www.prolec.energy | [6 empty] | Discovery | No - AI seeded
MVT-004 | WEG | MV Transformers | Distribution and power transformers (WEG Transformers USA); confirm three-phase 34.5 kV pad-mount offering | https://www.weg.net/institutional/US/en/ | [6 empty] | Discovery | No - AI seeded
MVT-005 | Virginia Transformer Corp | MV Transformers | E2X pad-mount; liquid substation/GSU (500 kVA–1,400 MVA); BESS listed as served industry | https://www.vatransformer.com | (540) 345-9892 | https://www.vatransformer.com |  |  |  |  | Discovery | No - AI seeded
MVT-006 | ERMCO | MV Transformers | Three-phase and single-phase pad-mount distribution transformers (incl. ECO-PAD) | https://www.ermco-eci.com |  | https://www.ermco-eci.com/ |  |  |  |  | Discovery | No - AI seeded
MVT-007 | Howard Industries | MV Transformers | Distribution transformers incl. large three-phase pad-mount 750–10,000 kVA (utilities, data centers, BESS) | https://www.howard.com | (601) 425-3151 | [5 empty] | Discovery | No - AI seeded
MVT-008 | Maddox Transformer | MV Transformers | New and remanufactured three-phase pad-mount and substation transformers; in-stock inventory | https://www.maddox.com | 1-800-270-2011 | https://www.maddox.com/contact |  |  |  |  | Discovery | No - AI seeded
MVT-009 | JST Power Equipment | MV Transformers | Liquid-filled pad-mount 1- and 3-phase (25–6,000 kVA, up to 35 kV); MV switchgear and packaged substations | https://www.jstpower.com |  | https://jstpower.com/contact/ |  |  |  |  | Discovery | No - AI seeded
MVT-010 | Sunbelt Solomon | MV Transformers | New and refurbished pad-mount and substation transformers; rentals and field services | https://www.sunbeltsolomon.com | 888-691-4712 | https://www.sunbeltsolomon.com/ |  |  |  |  | Discovery | No - AI seeded
HVB-001 | Hitachi Energy | HV Breakers | Dead tank circuit breakers up to 420 kV (incl. 362 kV); EconiQ SF6-free; PASS hybrid switchgear | https://www.hitachienergy.com/us/en | [6 empty] | Discovery | No - AI seeded
HVB-002 | Siemens Energy | HV Breakers | Dead tank breakers 72.5–550 kV (US SPS 362 kV); Blue SF6-free portfolio | https://siemens-energy.com/us/en/home.html |  | https://siemens-energy.com/us/en/home/products-services/product/dead-tank.html |  |  |  |  | Discovery | No - AI seeded
HVB-003 | GE Vernova | HV Breakers | Dead tank breakers up to 550 kV (DT1-362 for 362 kV); g3 SF6-free models (72.5/145 kV) | https://www.gevernova.com/grid-solutions/equipment/circuit-breakers/dead-tank-circuit-breakers | [6 empty] | Discovery | No - AI seeded
HVB-004 | Mitsubishi Electric Power Products (MEPPI) | HV Breakers | Dead tank gas circuit breakers 72.5–800 kV (362 kV up to 63 kA) | https://www.meppi.com |  | https://www.meppi.com/contact-us |  |  |  |  | Discovery | No - AI seeded
HVB-005 | Hyosung HICO | HV Breakers | Gas circuit breakers 72.5–800 kV | https://www.hyosungheavyindustries.com/en/business/power-products/P010104 | [6 empty] | Discovery | No - AI seeded
HVB-006 | HD Hyundai Electric (watchlist) | HV Breakers | SF6-free switchgear/breakers; 362 kV dead tank breaker planned for 2028 launch | [7 empty] | Discovery | No - AI seeded
MVB-001 | Eaton | MV Breakers / Switchgear | VacClad-HD 38 kV metal-clad switchgear with VCPW-HD vacuum breakers (1,200–3,000 A, up to 40 kA) | https://www.eaton.com/us/en-us.html | [6 empty] | Discovery | No - AI seeded
MVB-002 | Schneider Electric | MV Breakers / Switchgear | MV switchgear: air-insulated, gas-insulated and shielded solid insulation | https://www.se.com/us/en/ | [6 empty] | Discovery | No - AI seeded
MVB-003 | ABB | MV Breakers / Switchgear | MV breakers/switchgear and grid components (Electrification); confirm 38 kV outdoor breaker line | https://electrification.us.abb.com | [6 empty] | Discovery | No - AI seeded
MVB-004 | Siemens (Smart Infrastructure) | MV Breakers / Switchgear | SDV7 / SDV7-AR outdoor distribution vacuum breakers (15.5–38 kV, up to 40 kA, 200 kV BIL) | https://www.siemens.com/us/en.html | +1 (800) 347-6659 | [5 empty] | Discovery | No - AI seeded
MVB-005 | Powell Industries | MV Breakers / Switchgear | ANSI metal-clad (PowlVac, Power/Vac) and metal-enclosed switchgear; E-houses / PCR packaged solutions | https://www.powellind.com |  | https://www.powellind.com/contact |  |  |  |  | Discovery | No - AI seeded
MVB-006 | S&C Electric Company | MV Breakers / Switchgear | MV switching and protection (pad-mounted / metal-enclosed switchgear, distribution switching); confirm 34.5 kV collector-system products | https://www.sandc.com | [6 empty] | Discovery | No - AI seeded
MVB-007 | G&W Electric | MV Breakers / Switchgear | Switchgear, reclosers, overhead switches, current-limiting protection, cable accessories; confirm 38 kV ratings | https://www.gwelectric.com | [6 empty] | Discovery | No - AI seeded
EPC-001 | Mortenson | EPC Contractor | Full EPC for utility-scale BESS incl. project substation and gen-tie (e.g., Revolution 150 MW / 300 MWh, Crane TX, ERCOT) | https://www.mortenson.com | 763.522.2100 | https://www.mortenson.com/contact |  |  |  |  | Discovery | No - AI seeded
EPC-002 | McCarthy Building Companies | EPC Contractor | Renewable Energy & Storage group: utility-scale BESS and solar EPC | https://www.mccarthy.com | 314-968-3300 | https://www.mccarthy.com/contact-us |  |  |  |  | Discovery | No - AI seeded
EPC-003 | Blattner (Quanta Services) | EPC Contractor | Utility-scale wind, solar and energy storage construction/EPC incl. HV substation and collection | https://www.blattnercompany.com | 320-356-7351 | https://www.blattnercompany.com/contact |  |  |  |  | Discovery | No - AI seeded
EPC-004 | Burns & McDonnell | EPC Contractor | Self-perform EPC for BESS, substations and transmission; Texas BESS EPC references | https://www.burnsmcd.com | (816) 333-9400 | https://info.burnsmcd.com/contact-us |  |  |  |  | Discovery | No - AI seeded
EPC-005 | Primoris Services (Primoris Renewable Energy) | EPC Contractor | Utility-scale solar and BESS EPC; T&D/substation via Primoris T&D and Power Line Services | https://www.prim.com | (214) 740-5600 | https://www.prim.com/contact |  |  |  |  | Discovery | No - AI seeded
EPC-006 | Rosendin | EPC Contractor | Electrical contractor/EPC for utility-scale wind, solar, BESS and HV substation | https://www.rosendin.com | (408) 286-2800 | https://www.rosendin.com/contact/ |  |  |  |  | Discovery | No - AI seeded
EPC-007 | SOLV Energy | EPC Contractor | Utility-scale solar and BESS EPC, substation/HV, and O&M | https://solvenergy.com | 858.251.4888 | https://solvenergy.com/contact/ |  |  |  |  | Discovery | No - AI seeded
EPC-008 | MasTec Renewables (incl. former IEA, Wanzek, White Construction) | EPC Contractor | Utility-scale solar, wind and battery storage EPC; parent also provides transmission and substation (Power Delivery segment) | https://www.mastec.com | [6 empty] | Discovery | No - AI seeded
SW-001 | Tesla, Inc. (Tesla Energy) | Software | (a)/(b) Trading & BESS optimization - Autobidder (real-time trading and dispatch control platform) | https://www.tesla.com/support/energy/tesla-software/autobidder |  | https://www.tesla.com/contact |  |  |  |  | Discovery | No - AI seeded
SW-002 | Fluence Energy (Fluence Mosaic / Nispera) | Software | (a)/(b) Fluence Mosaic intelligent bidding software (launched in ERCOT Feb 2023); (c) Fluence Nispera APM | https://fluenceenergy.com |  | https://fluenceenergy.com/contact/ |  |  |  |  | Discovery | No - AI seeded
SW-003 | Ascend Analytics | Software | (a)/(d) SmartBidder (nodal price forecasting & bid optimization); Market Intelligence, PowerSIMM, PowerVAL | https://www.ascendanalytics.com | 1-303-415-1400 | https://www.ascendanalytics.com/about-us/lets-connect |  |  |  |  | Discovery | No - AI seeded
SW-004 | PCI Energy Solutions (Power Costs, Inc.) | Software | (a) ERCOT QSE / bid-to-bill - GenManager (forecast, ISO scheduling, settlements) and GenTrader (portfolio/storage optimization) | https://www.pcienergysolutions.com | +1 405.447.6933 | https://www.pcienergysolutions.com/contact-us/ |  |  |  |  | Discovery | No - AI seeded
SW-005 | Yes Energy | Software | (d) Market data & analytics (PowerSignals, QuickSignals, Live Power, Demand Forecasts, EnCompass); (a) bid-to-bill (PowerCore, Submission Services) | https://www.yesenergy.com | +1 303-993-2773 | https://www.yesenergy.com/locations |  |  |  |  | Discovery | No - AI seeded
SW-006 | Enverus | Software | (d) Market data & analytics / forecasting - Enverus Power & Renewables (Mosaic, Panorama, MarketView, Trading & Risk) | https://www.enverus.com | 1-800-282-4245 | https://www.enverus.com/contact-us/ |  |  |  |  | Discovery | No - AI seeded
SW-007 | Power Factors | Software | (c) Asset performance management / SCADA / EMS - Unity platform (Drive APM, local monitoring & controls) | https://www.powerfactors.com | 1-866-398-3010 | https://www.powerfactors.com/contact |  |  |  |  | Discovery | No - AI seeded
SW-008 | Habitat Energy | Software | (a)/(b) BESS optimization & trading service incl. Level 4 QSE services in ERCOT (EVOLVE) | https://www.habitat.energy |  | https://www.habitat.energy/contact |  |  |  |  | Discovery | No - AI seeded
SW-009 | Tyba | Software | (b)/(d) BESS simulation, automated dispatch/bidding and AI price forecasting platform | https://www.tyba.ai |  | https://www.tyba.ai/contact/ |  |  |  |  | Discovery | No - AI seeded
SW-010 | Modo Energy | Software | (d) Market data, BESS revenue benchmarks & forecasts (ERCOT coverage) | https://modoenergy.com | [6 empty] | Discovery | No - AI seeded
SW-011 | Stem, Inc. | Software | (b)/(c) PowerTrack Suite - PowerTrack EMS, PowerTrack Optimizer (formerly Athena), PowerTrack APM/monitoring (AlsoEnergy) | https://www.stem.com | 877-374-7836 | https://www.stem.com/contact/ |  |  |  |  | Discovery | No - AI seeded
SW-012 | Tenaska Power Services Co. (TPS) | Software | (a) QSE service provider - power marketing, 24/7 energy management, storage/renewable portfolio optimization, settlements | https://www.tenaska.com/our-business/power-marketing/ | 817-462-1521 | https://www.tenaska.com/contact-us/ |  |  |  |  | Discovery | No - AI seeded

## Key Items
Key Items
Default key items per vendor type (slots 1-10). RFI tabs use these as column headers. Edit a cell to change the default; type in a blank slot to add a key item.
Slot | Environmental Engineering | Civil Engineering | Structural Engineering | Electrical Engineering | Fire Protection Engineering | Owner's Engineer | Engineer of Record | Independent Engineer | BESS Equipment | MV Transformers | HV Breakers | MV Breakers / Switchgear | EPC Contractor | Software
1 | Permitting experience (TCEQ, USACE, TPWD) | Relevant BESS / substation site experience | BESS enclosure / substation structure experience | 345 kV / ERCOT interconnection experience | NFPA 855 / UL 9540A experience | BESS OE portfolio (MW / MWh) | 345 kV substation & collector design experience | Lender acceptance / bankability record | Lead time (weeks ARO) | Lead time (weeks ARO) | Lead time (weeks ARO) | Lead time (weeks ARO) | BESS & substation EPC experience (MW / MWh) | ERCOT QSE / market integration
2 | Relevant BESS / ERCOT project experience | Texas PE / firm registration | Texas PE / firm registration | Texas PE / firm registration | Hazard mitigation analysis (HMA) capability | Scope coverage (design review, FAT, site QA) | Texas PE / firm registration | BESS IE portfolio (MW / MWh) | FEOC compliance | FEOC compliance / country of origin | FEOC compliance / country of origin | FEOC compliance / country of origin | 345 kV self-perform capability | Cybersecurity (SOC 2, NERC CIP)
3 | Key personnel & availability | Key personnel & availability | Key personnel & availability | Studies capability (ETAP, PSCAD, PSS/E) | AHJ / fire marshal coordination in Texas | Key personnel & availability | Design tools (PLS-CADD, ETAP, AutoCAD) | Independence / conflicts | Cell chemistry & cell / module origin | Ratings & standards (IEEE C57, DOE efficiency) | Rating (362 kV class, interrupting kA) | Rating (kV class, kA, IEEE C37) | Bonding capacity | Hosting & data origin (FEOC)
4 | Fee basis / rate sheet | Fee basis / rate sheet | Fee basis / rate sheet | Key personnel & availability | Key personnel & availability | Independence / conflicts | Key personnel & availability | Key personnel & availability | Certifications (UL 9540, UL 9540A, NFPA 855) | Production capacity / slot availability | Insulating gas (SF6 / SF6-free) | Arc-resistant design | Safety record (EMR, TRIR) | Integration (SCADA, APIs)
5 | Insurance (PL / GL limits) | Insurance (PL / GL limits) | Insurance (PL / GL limits) | Fee basis / rate sheet | Fee basis / rate sheet | Fee basis / rate sheet | Fee basis / rate sheet | Fee basis | Warranty & performance guarantee | Factory testing & witness (FAT) | Utility / ERCOT references | Warranty | Financial strength | Pricing model
6 | Schedule capacity & turnaround | Schedule capacity & start date | Schedule capacity & start date | Insurance (PL / GL limits) | Insurance (PL / GL limits) | Insurance (PL / GL limits) | Insurance (PL limit) | Report turnaround | Domestic content (ITC adder) | Warranty | Warranty | Texas field service support | Texas labor availability | Support / SLA
7 | Texas office / field staff | Geotech / survey capability | Design software & standards (ASCE 7, ACI) | Schedule capacity & start date | Schedule capacity & turnaround | Texas / ERCOT presence | Schedule capacity & start date | Insurance (PL / GL limits) | Bankability / financial strength | Domestic content | Texas field service support |  | Risk appetite (LDs, wrap, insurance) | References
8
9
10
Blank slots = spare. A header typed directly on an RFI tab overrides the default for that RFI only.

## Projects
Projects
One row per Agentic project. RFI tabs pick their project from the Project Name column. Placeholder rows: rename them.
Project ID | Project Name | County / Location | ERCOT Load Zone | POI Voltage (kV) | Size (MW / MWh) | Project Manager | Status | Notes
PRJ-001 | Seven Angels BESS | [6 empty] | Placeholder added at setup 2026-10-05
PRJ-002 | Project B (placeholder - rename) | [6 empty] | Placeholder added at setup 2026-10-05
PRJ-003 | Project C (placeholder - rename) | [6 empty] | Placeholder added at setup 2026-10-05

## Lists
Lists
Dropdown values used across the workbook. Add owners in the yellow cells; change other lists only with a Change Log entry.
RFI Vendor Status | RFI Activity Status | Qualification Status | Key Item Rating | Action Owners (add names) | Vendor Types
Not Sent | Planning | Discovery | Meets | Jason Knedlhans | Environmental Engineering
Sent | Issued | Prequalified | Review / Risk | Sam Brandin | Civil Engineering
Acknowledged | Responses Due | Qualified | Fails | Matt Shae | Structural Engineering
Clarifications Open | Evaluation | AVL | Not Rated | Project Manager | Electrical Engineering
Response Received | Closed - Advance to RFP | On Hold |  | Project Engineer | Fire Protection Engineering
Under Review | Closed - No Further Action | Disqualified |  | Vendor | Owner's Engineer
Complete | Cancelled |  |  |  | Engineer of Record
Declined |  |  |  |  | Independent Engineer
No Response |  |  |  |  | BESS Equipment
MV Transformers
HV Breakers
MV Breakers / Switchgear
EPC Contractor
Software

## Change Log
Change Log
Record every structural change (tabs, columns, lists, key item defaults, formulas) and each new RFI tab. Routine data entry is covered by SharePoint version history.
Date | Version | Changed By | Tab / Area | Change | Reason / Approved By
2026-10-05 | 1.0 | Claude (AI) for Jason Knedlhans | All | Initial release. Replaces the HTML RFI tracker (claude.ai artifact, retired). Tabs: Read Me, Dashboard, RFI Register, RFI-001 (example), RFI_TEMPLATE, Vendors (109 vendors from vendor landscape tracker), Key Items, Projects (placeholders), Lists, Change Log. | Requested by Jason Knedlhans; pending review